# Business Case: Darwinbox HRIS

Al Liwan Group  |  January 2026

Requested by: David Orban, Head of IT / Tracey Batty-Jones, HR

Budget: ~$42,000-$60,000 USD (AED 154,140-220,200) Year 1

# Executive Summary

Al Liwan Group requires a lightweight HRIS system for Q1 2026 deployment that can operate until full ERP implementation (targeted Q4 2026+). Following a structured evaluation against regulatory, architectural, and operational gates, Darwinbox emerges as the only candidate that passes all three gates.

This is a Phase 1 interim solution with a clear migration path to Dynamics 365 when the organization is ready for full ERP deployment.

# Evaluation Summary

## Gate Results Summary

| Vendor | Gate 1 Reg. | Gate 2 Arch. | Gate 3 Ops. | Status |
| --- | --- | --- | --- | --- |
| Microsoft D365 | ✅ Pass | ✅ Pass | ❌ Fail | Deferred (Phase 2) |
| HiBob | ✅ Pass | ❌ Fail (EU/US) | ✅ Pass | Excluded |
| Darwinbox | ✅ Pass | ✅ Pass | ✅ Pass | Qualified |
| BambooHR | ✅ Pass | ❌ Fail (US) | ✅ Pass | Excluded |

- HiBob and BambooHR fail on UAE data residency — neither offers Middle East hosting

- Dynamics 365 fails Gate 3 — requires significant build effort, not suitable for Q1 HRIS-only deployment

Darwinbox is the only candidate passing all three gates.

# Darwinbox in Regulated UAE Organizations

## Regional Presence & Credentials

| Aspect | Details |
| --- | --- |
| Regional Office | Dubai International Financial Centre (DIFC) |
| GCC Coverage | UAE, Saudi Arabia, Bahrain, Kuwait, Oman, Qatar |
| Regional Customers | Lulu Group, Aramex, Mobily Infotech |
| Global Customers | Nivea, Starbucks, Sephora, Zara, AXA |
| Scale | 1.5M+ employees across 650+ enterprises globally |
| Unicorn Status | Achieved in 2023 with $72M funding round |
| Regional Partner | PwC Middle East (preferred implementation partner) |

## Security & Compliance

| Certification | Status | Relevance |
| --- | --- | --- |
| ISO 27001 | ✅ Certified | Information security management |
| SOC 2 Type II | ✅ Certified | Security controls attestation |
| ISO 27701 | ✅ Certified | Privacy information management |
| GDPR | ✅ Compliant | Data protection standard |
| UAE Labor Law | ✅ Supported | GCC-specific compliance |

# Cost Analysis

## Year 1 Total Cost Model

| Scenario | Licensing | Implementation | Total (USD) | Total (AED) |
| --- | --- | --- | --- | --- |
| Conservative | $10,000 | $15,000 | $25,000 | 91,750 |
| Baseline | $15,000 | $27,000 | $42,000 | 154,140 |
| Growth | $18,000 | $42,000 | $60,000 | 220,200 |

## Ongoing Annual Cost (Year 2+)

| Scenario | Annual Licensing | Annual Support | Total (USD) |
| --- | --- | --- | --- |
| Conservative | $10,000 | $2,000 | $12,000 |
| Baseline | $15,000 | $3,000 | $18,000 |
| Growth | $22,500 | $4,500 | $27,000 |

# Implementation Timeline

Target: Production by end of Q1 2026

| Phase | Duration | Activities |
| --- | --- | --- |
| Week 1-2 | 2 weeks | Contract, environment setup, data mapping |
| Week 3-6 | 4 weeks | Configuration, data migration, SSO integration |
| Week 7-8 | 2 weeks | UAT, training, go-live preparation |
| Week 9-10 | 2 weeks | Go-live, hypercare support |

Total: ~10 weeks (within 90-day Gate 3 requirement)

# Risk Assessment

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Implementation delay | Medium | Medium | PwC partnership provides experienced local resources |
| Integration complexity | Low | Medium | Native Entra ID SSO support; documented APIs |
| Vendor lock-in | Low | Low | Clean data export; API-first architecture |
| Feature gaps vs D365 | Medium | Low | Phase 1 focuses on core HR; advanced in Phase 2 |
| Regional support quality | Low | Medium | DIFC office; PwC local partner |

# Recommendation

Approve Darwinbox HRIS for Phase 1 deployment.

## Next Steps

- Request formal quote from Darwinbox for 56-75 employees

- Engage PwC Middle East for implementation scoping

- Schedule technical demo with IT team

- Confirm Entra ID SSO integration requirements

- Target contract signature by end of January 2026